## User Stories
Team name | Overflow | Guidelines | 1. Sort the user stories according to priority
Project | Lirten Hub |  | 2. Priority refers to how fundamental is the user story for the project ( For example : you cannot implement Sumerge without "add investor" user story )
Module | Module : Oppurtunity SubModule : Vacancy Module : Portofolio SubModule: Life Coaching Module : Profile SubModule:Member and Partner |  | 3. For everyone: Registration and log-in will be implemented in later sprints (~ Sprint 3) - this is when we will cover this material in Labs
Scrum ID | 40-1493 |  | 4. Use the unique ID to structure the user stories. For example: If (1) is "Portfolio Development" module, then 1.1 and 1.2 … are the related user stories
Scrum Email | philip.sidhom@student.guc.edu.eg |  | 5. Only features to be implemented in later sprints can be left as epics.
Uniuqe ID | User story | Epic ? | Priority (high/medium/low)
1 | Vacancy SubModule
1.1 | As a partner,I am able to submit a description(monthly wage, the location of the job, the required daily hours) and duration of a full time job. |  | high
1.2 | As an admin,I am able to view the description and duration of full time jobs |  | high
1.3 | As an admin, I am able to post full time jobs for members to apply |  | high
1.4 | As a member,I am able to view jobs |  | high
1.5 | As a member,I am able to apply for jobs |  | high
1.6 | As a member,I am able to search jobs |  | medium
1.7 | As a member, I am able to view recommendations for full-time jobs based onhis skills/locations/availability |  | medium
1.8 | As a partner/admin,I am able to view the current state of the job |  | medium
1.9 | As a partner,I am able to edit a submitted vacancy |  | medium
1.1 | As an admin, I am able to approve an edit to a submitted vacancy |  | medium
1.11 | As a partner,I am able to message the admins in order to negotiate the attributes of the job |  | low
1.12 | As an admin,I am able to message the partner in order to negotiate the attributes of the job |  | low
2 | Life Coaching SubModule
2.1 | As a life coach,I am able to post my weekly schedule on the system |  | high
2.2 | As a member, I am able to book appointments with a life coach in available slots |  | high
2.3 | As a member, I am able to view booked/free/confirmed slots on the system for all life coaches |  | high
2.4 | As a life coach, I am able to view my booked/free/confirmed slots on the system |  | high
2.5 | As a life coach, I am able to confirm an appointment with a member |  | high
2.6 | As a life coach, I am able to receive notifications when a certain time slot is booked |  | medium
2.7 | As a life coach/member, I am able to suggest a location for an appointment |  | medium
2.8 | As a life coach/member, I am able to confirm a location for an appointment |  | medium
2.9 | As a member, I am able to receive a notification confirming my booking with a life coach |  | medium
3 | Member,Partner and Life Coach Profiles
3.1 | As a member/partner, I am able to register on the system |  | high
3.2 | As a member/partner, I am able to sign in on the system |  | high
3.3 | As an admin, I am able to approve partners |  | high
3.4 | As a member, I am able to view/edit my profile info(name, age, skills, interests) |  | high
3.5 | As a member, I am able to view ( past events , projects/tasks/jobs completed, reviews and certificates/masterclasses). |  | high
3.6 | As an admin, I am able to set a location and time to sign the contract and agreements with a partner/life coach |  | high
3.7 | As a partner, I am able to review a member who completed a task for me |  | medium
3.8 | As a partner, I am able to view/edit my profile (business information, partners,board members, events , field of work) and view open vacancies and past projects |  | medium
3.9 | As a partner, I am able to view feedback received by members |  | medium
3.1 | As a member, I am able to submit feedback to a partner I completed a task for |  | medium
3.11 | As a life coach,I am able to view/edit my profile(name,age,field of work) and view (past appointments and reviews) |  | medium
3.12 | As a member,I am able to review a life coach I have worked with |  | medium
3.13 | As a partner/life coach, I am able to receive a notification with the time and location to sign a contract |  | medium
3.14 | As a partner/life coach, I am able to message the admins to change the location or time of contract meeting |  | low

## Sprint1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | Notes
1 | As a super admin, I am able to CRUD admins | 1 | Youssef Shafei | N/A | N/A
2 | As an admin, I am able to CRUD partners | 1 | Farah Hazem | N/A | N/A
3 | As an admin, I am able to CRUD life coaches | 1 | Ahmed Yasser | N/A | N/A
4 | As an admin, I am able to CRUD members | 1 | Omar Nael | N/A | N/A
5 | As a partner/admin, I am able to CRUD full time jobs | 1 | Philip Mouris | N/A | N/A
6 | As a member, I am able to read full time jobs | 0 |  | N/A | N/A | Repeated
7 | As an admin, I am able to CRUD job applications | 1 | Youssef Sherif | N/A | N/A
8 | As a member, I am able to create job applications | 0 |  | N/A | N/A | Repeated
9 | As a life coach/admin, I am able to CRUD slots in schedule | 1 | Youssef Samy | N/A | N/A
10 | As a member, I am able to read slots in life coaches' schedules | 0 |  | N/A | N/A | Repeated
11 | As a member/partner/life coach, I am able to CRUD my profile | 0 |  | N/A | N/A | Repeated
12 | As a partner/admin, I am able to CRUD reviews | 1 | Youssef Fathi | N/A | N/A
13 | As a member/admin, I am able to CRUD feedbacks | 1 | Abdellatif Emara | N/A | N/A
9

## Models
Entity Name
Admin | name | dateOfBirth | gender | joinDate | salary | email | super
Partner | name | address | email | fax | phone | partners | members | fieldOfWork | projects | feedback [Array of feedbacks]
Life Coach | name | dateOfBirth | gender | joinDate | hourlyRate | email | monthlySlots [Array of slots]
Member | name | dateOfBirth | gender | joinDate | email | skills [Array of Strings] | interests [Array of Strings] | reviews[array of reviews]
Vacancy | Partner[Entity] | description | duration | monthlyWage | location | dailyHours | startDate | endDate | state | acceptedMember
Job Applications | partner[Entity] | vacancy[Entity] | member[Entity] | datePosted | text
Reviews | partner[Entity] | review | rating[Integer] | datePosted
Feedback | member[Entity] | feedback[String] | datePosted
Slots | booked | date | location | member[Entity] | confirmed